## Income
CIL - Income
Date Received | Amount | Deadline For Spending
29th April 2021 | 25059.6 | 29th April 2026
16th November 2021 | 13350.59 | 16th November 2026
26th April 2022 | 19549.39 | 26th April 2027
26th October 2022 | 12049.39 | 26th October 2027
24th April 2023 | 12049.39 | 24th April 2028
2023-10-01 | 0 | N/a
82058.36

## Ongoing
CIL Summary of agreed projects Dec 2023 (Net Costs)
Project | Location | Cost (Net) | Installation Costs (Net) | Who Is Responsible For Installation | Est Time of Completion | Maintenance Costs | Quantity | Total (Net) | Approved | Notes / Actions
Benches (Non-Backed) | Jubilee Wood | 380 | £270 - Including Slab | Jon Holmes (WDC) |  | £150 - one off lifetime | 2 | 1600 | 20th January 2022 (FC) | Ordered 28th November 23 - contact is Tom Crawford WCC County Parks & Green Spaces, operations manager. Due for delivery to WTC 16th January to be stored until weather permits installation.
Wayfinding | Warwick wayfinding | 47500 | N/A | Heath Whybrow Pedrola | Ongoing |  | 1 | 47500 | Oct 2023 (F&P) | No Action Required At The Moment
49100

## Cllr Requests
CIL Councillor Requests
Councillor | Request | Location | Notes/Actions
Oliver Jacques | Bench | On pavement by bus stop, Spinney Hill | WCC Highways has given permission - £567.50
| Grit bin x2 | Scar Bank by the canal | WCC Highways has not given permission - does not meet gradient requirements
Daniel Browne | Replacement windows in existing noticeboard | Nr Chase Meadow Community Centre | Quote from WDC via their contractor is £250
Simon Pargeter | Bench | Wedgnock Green, on side of green space | WCC Highways has given permission - £567.50
| Bench | Outside the Packmores Centre | WDC Housing has given permission - £567.50
Kathleen Gorman | Traffic speed survey | Fusiliers Way | WCC Traffic Surveys Team has confirmed this is deliverable via their team - £220
Paul Wightman | Grit bin (to replace existing) | Crane Close, Woodloes | Awaiting response from WCC Highways - £126.64
Total = £2299.14
Simon Pargeter | New signage | Priory Park | WDC owned park - therefore their permission would be needed. Info needed re type of information to be included, type and no. of signs and proposed locations.

## Completed & Paid
CIL Summary of agreed projects January 2024 (Net Costs)
Project | Location | Cost (Net) | Installation Costs (Net) | Who Is Responsible For Installation | Est Time of Completion | Maintenance Costs | Quantity | Total (Net) | Approved | Notes | Actions
Defibrillator | The Court House | 1825 | N/A | Defib Machines | 5th May 2022 | - | 1 | £1,825 (total cost over the 5 years) | 20th January 2022 (FC) | 5 Year Service Lease. Installed 5th May 2022 | Completed | Paid to end April 2023 - £953.40
Warwick In Bloom | Emscote Road & Sainsbury's | 1273.08 | Amberol Costs | Barn Close Nurseries | 2022-06-01 | - | 9 | 2446.33 | April 2022 (C&C / E&T) | Completed
|  | 803.25 | Barn Close Costs | [6 empty] | Completed
|  | 370 | WDC Costs |  |  | £30 Watering Each |  |  |  | Completed
Bench | Pageant Gardens | 383.33 | Corido - Bench | WTC | 2022-09-01 | - | 1 | 420 | Completed
|  | 25 | Spa Trophies - Plaque |  |  |  |  | 25
Daffodil Bulbs | Emscote Road | £43.33 (25kg) | - | WTC | 2022-10-01 | - | 1 X £25kg | 43.33 | Completed
Tree Planting |  | 1995 | Included | WCC | 2022-11-01 |  | 8 | 1995 | Installation completed (needs plaque)
Grit bin | Outside Newburgh Primary School | 119.88 |  | WCC | End of April 23 |  | 1 | 119.88 | Completed
WTC Logos | Grit bins | 18 |  | WTC | 2023-04-01 |  | 4 | 18 | Completed
Defibrillator | 7th Warwick (Woodloes) Scout Group - Scout Hut | 978 | N/a | 7th Warwick (Woodloes) Scout Group | 2023-05-01 |  | 1 | 978 | 14th March 2023 F&P | Funding passed to Scouts group - April 2023 | Completed
Wayfinding | Warwick Town Centre | 13500 | - | Whybrow Pedrola | End of 2023 | - | 1 | 13500 | Ongoing project - total amount paid so far
Bench | Theatre St | 356 | 200 | Koelman Groundworks | 2023-08-01 | As and when necessary | 1 | 556 | 14th March 2023 F&P | Completed
Noticeboard | Shakespeare Avenue | 1257.5 | 150 | Koelman Groundworks | 2023-10-01 | As and when necessary | 1 | 1407.5 | 14th March 2023 F&P | Completed
Noticeboard | Eastley Crescent | 1257.5 | 150 | Koelman Groundworks | 2023-10-01 | As and when necessary | 1 | 1407.5 | 14th March 2023 F&P | Completed
Bench | Reardon Court | 356 | £200 (paid for by Woodloes Community Centre Management Committee) | Koelman Groundworks | 2023-08-01 | As and when necessary | 1 | 356 | 14th March 2023 F&P | Completed
Defibrillator | The Gap Community Centre | 1803.2 | N/a | The Gap Community Centre | 2023-12-01 | N/a | 1 | 1803.2 | 12th Oct 2023 F&P | Funding passed to The Gap - Nov 2023 | Completed
Grit bin | Replacement for existing by underpass, Priory Pools | 126.64 | N/a | WCC | 2023-12-01 | As and when necessary | 1 | 126.64 | 12th Oct 2023 F&P | Completed
Grit bin | Bottom of hill at Blacklow Rd, nr road name sign | 126.64 | N/a | WCC | 2023-12-01 | As and when necessary | 1 | 126.64 | 12th Oct 2023 F&P | Completed
Bench | Bottom of Blacklow Rd - replacing existing | 367.5 | 200 | Koelman Groundworks | 2024-01-01 | As and when necessary | 1 | 567.5 | 12th Oct 2023 F&P | To be completed by 12th Jan 2024
Bench | Outside Castle Hill almshouses | 367.5 | 200 | Koelman Groundworks | 2024-01-01 | As and when necessary | 1 | 567.5 | 12th Oct 2023 F&P | To be completed by 12th Jan 2024
Noticeboard | Junction of Greville Rd and Emscote Rd by bus shelter | 1300 | 150 | Koelman Groundworks | 2024-01-01 | As and when necessary | 1 | 1450 | 12th Oct 2023 F&P | To be completed by 12th Jan 2024
29739.02
£3,219.34 unallocated